## Team_Pipeline
Team_Member_Name | Email_BBK | Status | Definition | Proposed Team Name | Proposed by | Carys | Gary | William | Mei Len | Samuel | Toby | Vote Count
Carys Williams | cwilli46@student.bbk.ac.uk | Backlog | Task Identified | DataForge Analytics | Mei Len | [6 empty] | 0
Gary Murphy | gmurph05@student.bbk.ac.uk | Planned | Task Scheduled | The Scalables | Mei Len | [6 empty] | 0
William Mckenna | wmcken01@student.bbk.ac.uk | In Progress | Task started | Parallel Minds | Mei Len | [6 empty] | 0
Mei Len Vorkel | mvorke01@student.bbk.ac.uk | Completed | Task completed | Byte Cohort | Mei Len | [6 empty] | 0
Samuel Weldemariam | swelde03@student.bbk.ac.uk | Cancelled | Task cancelled | The Data Streamers | Mei Len | [6 empty] | 0
Toby Lock | tlock01@student.bbk.ac.uk | Blocked | Task unable to progress | Analytix | Mei Len | [6 empty] | 0
|  | Overdue | Task Overdue | DataHive | Mei Len | [6 empty] | 0
Github Emails |  |  |  | Insight Engine | Mei Len |  | 1 |  |  |  |  | 1
Team_Member_Name | Email (Github) |  |  | The Pipeline | Mei Len | 1 |  | 1 | 1 | 1 | 1 | 5
Carys Williams | carysewilliams7@gmail.com |  |  | The Schema Team | Mei Len | [5 empty] | 1 | 1
Gary Murphy | gmurph05@student.bbk.ac.uk |  |  | Indexing Agents | Mei Len | [6 empty] | 0
William Mckenna | wmpmck@googlemail.com |  |  | Team Big DAWG (Big Data Analytics Working Group) | Gary | [6 empty] | 0
Mei Len Vorkel |  |  |  | The NOISE Makers (Network of Optimized Inference & Speech Engineers) | Gary | [6 empty] | 0
Samuel Weldemariam | samuelweldeluel2021@gmail.com |  |  | Team BARK ( Big Data Audio Reconciliation Kit) | Gary | [6 empty] | 0
Toby Lock | tobylock68@gmail.com |  |  | Data cleaning and Recommendation system for studio Ghibi Movies | Samuel | [6 empty] | 0
|  |  |  | Team XXX | [7 empty] | 0
|  |  |  | Team XXX | [7 empty] | 0
|  |  |  | Team XXX | [7 empty] | 0
|  |  |  | Team XXX | [7 empty] | 0
|  |  |  | Team XXX | [7 empty] | 0
|  |  |  | Team XXX | [7 empty] | 0
|  |  |  | Team XXX | [7 empty] | 0
|  |  |  | Team XXX | [7 empty] | 0

## Project Schedule
Sequence No. | Phase | Task | Assignee | Start Date | End Date | Days Count | Status | Deliverable | Notes
1 | Phase 1: Setup | Intro Meeting | All | 2026-05-04 | 2026-05-05 | 1 | Completed | Project Plan | Bank Holiday = Mon, 4-May-2026 Decide on Team Name & Assign Tasks Decide on in-person meet-up date/time/venue
2 | Phase 1: Setup | Initialize GitHub Repo & invite steliosot | Mei Len Vorkel | 2026-05-04 | 2026-05-05 | 1 | Completed | Repo URL | Mei Len Vorkel offered to do this in the group chat (2026-05-02). Team Name needed. All to confirm
3 | Phase 1: Setup | Install Vosk & Geminilocal env | All | 2026-05-04 | 2026-05-10 | 6 | Completed | Env ready | Team to decide between Gemini & Ollama first. Set up the vosk-model-en-us-0.22-lgraph. Vosk to be used for transcription
4 | Phase 1: Setup | Team Recording Session (30+ turns) | All | 2026-05-04 | 2026-05-10 | 6 | Completed | Raw Audio/CSV | All 6 members record at least 5 audio phrases each (total 30+ rows) to ensure you exceed the 25-row minimum. (See Script tab in this file for individual speaker text) (perhaps complete in kick-off meeting - if it is recorded)
5 | Milestone Meeting | Phase 1 Closeout & Phase 2 Intro | All | 2026-05-11 | 2026-05-11 | 0 | Cancelled | Project Plan | Monday evening at 6 or 7 pm for 30min (There is no BDA class on this Monday) ***THIS IS A PLACEHOLDER. WE MAY NOT NEED IT*** This is to confirm that the Phase 2 team have everything they need and to resolve any outstanding issues
6 | Phase 2: Development | Stage 1: Vosk Microphone Script | Data Engineers | 2026-05-11 | 2026-05-17 | 6 | Completed | raw_vosk_text | create a python script that outputs the initial timestamp, name, raw_text_vosk, and time_taken_sec.
7 | Phase 2: Development | Stage 2: AI Correction Integration | Data Engineers | 2026-05-11 | 2026-05-17 | 6 | Completed | text (corrected) | Implement the Gemini script to clean up the Vosk output into the text column.
8 | Phase 2: Development | Stage 3: Python Feature Enrichment | AI & Logic Devs | 2026-05-11 | 2026-05-17 | 6 | Completed | Enriched CSV | Write the Python functions for -question_flag, -num_words, -speech_rate_wps, -speaker_turn Connect Phase 1 and Phase 2 so the data flows from audio > transcription > AI > enrichment > CSV.
9 | Milestone Meeting | Phase 2 Closeout & Phase 3 Intro | All | 2026-05-17 | 2026-05-18 | 1 | Cancelled | Project Plan | 30min - Time TBD (We have a class on 18-May-2026) ***THIS IS A PLACEHOLDER. WE MAY NOT NEED IT*** This is to confirm that the Phase 3 team have everything they need and to resolve any outstanding issues
10 | Phase 3: Logic | Stage 4: CSV Validation Script | AI & Logic Devs | 2026-05-18 | 2026-05-24 | 6 | Completed | Validation Logs | Write the logic to check for missing values, valid datetimes, and numeric constraints
11 | Phase 3: Logic | Stage 5: Analytics & Stats Output | AI & Logic Devs | 2026-05-18 | 2026-05-24 | 6 | Completed | Final Analytics | Calculate the "Top 5 Speakers," "Average Speech Rate," and "Question Counts."
12 | Phase 4: Finalize | Complexity Analysis & README | QA & Documentation | 2026-05-18 | 2026-05-24 | 6 | Completed | README.md | Draft the README section explaining Big O notation for your processing (e.g., O(n) for CSV parsing).
13 | Phase 4: Finalize | Record Team Video Presentation | All (Led by QA & Documentation Team) Or Individuals record and then hand to QA & Doc team | 2026-05-25 | 2026-05-25 | 0 | Completed | Video MP4/Link | Record a screen-share demo and have each member explain their contribution (per Section 10). (***NOTE: THE INDIVIDUAL ASSIGNMENT IS MADE AVAILABLE THIS WEEK***)
14 | Phase 4: Finalize | Edit and Finalize Team Video Presentation | QA & Documentation | 2026-05-26 | 2026-05-31 | 5 | Completed | Video MP4/Link | NOTE: Mon, 25-May-2026 is a Bank Holiday Compile edit. Add captions, etc.
15 | Milestone Meeting | Phase 4 Closeout | All | 2026-06-01 | 2026-06-02 | 1 | Cancelled | Project Plan | Monday evening at 6 or 7 pm for 30min (There is no BDA class on this Monday) ***THIS IS A PLACEHOLDER. WE MAY NOT NEED IT*** This is to confirm that all phases are closed and that we have everything for 'submission'.
16 | Phase 4: Finalize | Final Submission & Peer Forms | Individual | 2026-06-01 | 2026-06-02 | 1 | Completed | PDF/GitHub | Ensure everyone has their individual Peer_Evaluation_Form.docx ready. Do NOT review yourself. (Peer reviews DO NOT go on GitHub)
17 | Phase 4: Finalize | (**Buffer Time - for any outstanding tasks**) |  | 2026-06-02 | 2026-06-16 | 14 | Cancelled
18 | Submission Due |  |  | 2026-06-17 | 2026-06-17 | 0 | Planned |  | The End.
|  |  |  | Total Project Days | 29

## Role Matrix
Role | Team_Member_Pair | Task
Data Engineers | Member 1 & 2 | Vosk setup, Audio recording, Raw CSV output
AI & Logic Devs | Member 3 & 4 | Gemini/Ollama API, Transcript cleaning, Feature enrichment
QA & Documentation | Member 5 & 6 | Validation script, Analytics, Complexity report, Video editing
Role | Team_Member_No | Team_Member_Name
Data Engineers | Member 1 | Toby Lock
Data Engineers | Member 2 | William Mckenna
AI & Logic Devs | Member 3 | Carys Williams
AI & Logic Devs | Member 4 | Mei Len Vorkel
QA & Documentation | Member 5 | Gary Murphy
QA & Documentation | Member 6 | Samuel Weldemariam

## Script
Team Assignment Script ¦ 30 Turns
Option 1 - Sequential |  |  |  | Option 2 - Non-Sequential
Turn Count | Speaker_Number | Team_Member_Name | Speech | Turn Count | Speaker_Number | Team_Member_Name | Speech
1 | Speaker 1 | Carys Williams | Alright team, let's get this growth meeting started. We need to look at our Q3 scaling targets. | 1 | Speaker 1 | Gary Murphy | Alright everyone, thanks for joining. Let's look at our growth strategy for the mobile app.
2 | Speaker 1 | Carys Williams | The current roadmap shows a 20 percent increase in active users, but are we ready for that load? | 2 | Speaker 2 | Carys Williams | I've been tracking user sign-ups, and while they're up, the conversion from free to paid is low.
3 | Speaker 1 | Carys Williams | I want to ensure our vision for the mobile app aligns with our actual developer capacity. | 3 | Speaker 3 | William Mckenna | I think the onboarding flow is the bottleneck; it's currently taking users too long to find the value.
4 | Speaker 1 | Carys Williams | Before we dive into the details, did everyone have a chance to review the agenda I sent out? | 4 | Speaker 1 | Gary Murphy | That's a fair point. Carys, what does the pricing feedback look like from those early users?
5 | Speaker All | All Members | (Various) | 5 | Speaker 2 | Carys Williams | They love the features but find the entry price steep. I'm thinking about a student discount tier.
6 | Speaker 1 | Carys Williams | Great. Let's start with the financial outlook and our current burn rate. | 6 | Speaker 4 | Mei Len Vorkel | If we add a student tier, we'll need to update the API to verify academic email addresses.
7 | Speaker 2 | Toby Lock | On the sales side, we are seeing a lot of interest from the education sector. | 7 | Speaker 5 | Samuel Weldemariam | And from a marketing perspective, we'd need to target universities directly on social media.
8 | Speaker 2 | Toby Lock | I'm proposing a student discount tier to capture that demographic before our competitors do. | 8 | Speaker 3 | William Mckenna | Before we go that far, can we fix the login bug? It's still crashing for some Android users.
9 | Speaker 2 | Toby Lock | Can we target students first with a 50 percent reduction for the first six months? | 9 | Speaker 4 | Mei Len Vorkel | I have a patch ready for that, but we need to run a full penetration test on the new build first.
10 | Speaker 2 | Toby Lock | Early users are complaining about the high entry price for the premium features. | 10 | Speaker 6 | Toby Lock | I've allocated budget for the security audit, but we need to decide if we're hiring more devs.
11 | Speaker 2 | Toby Lock | If we lower pricing for the first 100 sign-ups, we can gather much better testimonial data. | 11 | Speaker 1 | Gary Murphy | Growth is our priority. If the tech debt is slowing us down, we hire. Mei Len, what's your take?
12 | Speaker 3 | Mei Len Vorkel | I've been looking at the app interface, and the onboarding flow is still a bit clunky. | 12 | Speaker 4 | Mei Len Vorkel | We definitely need a backend specialist if we plan on horizontal scaling by Q4.
13 | Speaker 3 | Mei Len Vorkel | We fixed the bug where the login button would disappear on smaller screens. | 13 | Speaker 5 | Samuel Weldemariam | If we hire now, I can start building the brand story around our new 'speed and security' focus.
14 | Speaker 3 | Mei Len Vorkel | However, the user experience during the file upload process needs a complete overhaul. | 14 | Speaker 2 | Carys Williams | Wait, if we change the messaging, will that affect our current SEO rankings for 'meeting analytics'?
15 | Speaker 3 | Mei Len Vorkel | Does the design team have the new mockups ready for the dashboard? | 15 | Speaker 5 | Samuel Weldemariam | It shouldn't, as long as we keep the core keywords in our meta descriptions and blogs.
16 | Speaker 3 | Mei Len Vorkel | I really think we need to prioritize accessibility features in the next sprint. | 16 | Speaker 3 | William Mckenna | I'm more worried about the UI. Should the dashboard show analytics first or the recording list?
17 | Speaker 4 | William Mckenna | Technically speaking, our API integration with the cloud provider is finally stable. | 17 | Speaker 1 | Gary Murphy | Let's go with analytics first. That's our unique selling point compared to the competitors.
18 | Speaker 4 | William Mckenna | But if we scale to 10,000 users, we're going to need better database horizontal scaling. | 18 | Speaker 6 | Toby Lock | Regarding the office, the lease is up for renewal. Should we stay remote or get a hub?
19 | Speaker 4 | William Mckenna | I'm worried about the load balancing during peak morning hours in the US. | 19 | Speaker 2 | Carys Williams | Actually, most of the sales team prefers a hybrid model. It helps with client calls.
20 | Speaker 4 | William Mckenna | Should we consider moving our hosting to a more localized server for European users? | 20 | Speaker 3 | William Mckenna | I'm happy as long as I don't have to commute every day. The current setup works for design.
21 | Speaker 4 | William Mckenna | The security updates have been patched, but we need to run a full penetration test next week. | 21 | Speaker 1 | Gary Murphy | Let's look into a smaller hub. Toby, can you get us some quotes by our next meeting?
22 | Speaker 5 | Samuel Weldemariam | Our SEO progress has been steady, but our social media ads are underperforming. | 22 | Speaker 6 | Toby Lock | Will do. I'll also update the budget for the new API tools Mei Len mentioned earlier.
23 | Speaker 5 | Samuel Weldemariam | I want to refocus our marketing budget toward TikTok and Instagram influencers. | 23 | Speaker 4 | Mei Len Vorkel | Thanks. I'll start the documentation for the database migration tonight.
24 | Speaker 5 | Samuel Weldemariam | Does the email campaign have a high enough click-through rate to justify the cost? | 24 | Speaker 5 | Samuel Weldemariam | I'll coordinate with Carys on the pricing copy for the new student landing page.
25 | Speaker 5 | Samuel Weldemariam | We need to simplify the brand messaging so it's clear we are a 'meeting analytics' tool. | 25 | Speaker 1 | Gary Murphy | Excellent. Does anyone have any other blockers before we wrap up for the day?
26 | Speaker 5 | Samuel Weldemariam | I'll have a full report on the acquisition costs by Friday morning. | 26 | Speaker 3 | William Mckenna | Just a reminder that the new mockups are in the shared folder for everyone to review.
27 | Speaker 6 | Gary Murphy | I've updated the budget allocation for the next quarter to include three new engineering hires. | 27 | Speaker 4 | Mei Len Vorkel | Got it. I'll check the specs to make sure the load times stay under two seconds.
28 | Speaker 6 | Gary Murphy | We need to finalize the office lease agreement before the end of the month. | 28 | Speaker 2 | Carys Williams | I'll send the updated sales forecast to Toby after this call.
29 | Speaker 6 | Gary Murphy | Are we all in agreement that the next all-hands meeting should be on June 13th? | 29 | Speaker 6 | Toby Lock | Perfect. I'll have the final financial summary ready for our all-hands on June 13th.
30 | Speaker 6 | Gary Murphy | I'll send out the summary notes and task assignments by EOD. | 30 | Speaker 1 | Gary Murphy | Great work today, team. Let's execute on these items and meet again next week. Meeting adjourned.
31 | Speaker 6 | Gary Murphy | If there's nothing else, I think we can adjourn for today. Good work everyone. |  |  |  | C

## Tech Stack
https://github.com/warestack/bda/blob/main/team-project/README.md
3. Recommended technologies
Use:
Python
Vosk speech recognition
Vosk model: vosk-model-en-us-0.22-lgraph (128M)
Gemini API for transcript correction
CSV files for storing the dataset
IDE = VS Code
Screen Recording = Microsoft Teams (Individual Meetings)
Video Editing = DaVinci Resolve

## Data Schema (CSV Structure)
Column Name | Source | Type | Description/Logic | Task Start | Task End | Role | Name
timestamp | Vosk Script | Datetime | ISO format timestamp of the turn
name | Vosk Script | String | Name of the speaker
raw_text_vosk | Vosk Script | String | Original transcript from Vosk (imperfect)
text | AI Model | String | AI corrected version of raw_text_vosk
time_taken_sec | Vosk Script | Float | Duration of the speech segment
question_flag | Python Logic | Boolean | True if text ends with '?'
num_words | Python Logic | Integer | Word count of the corrected text
text_size_chars | Python Logic | Integer | Character count of the corrected text
speech_rate_wps | Python Logic | Float | num_words / time_taken_sec
speaker_turn_id | Python Logic | Integer | Cumulative turn count per speaker
https://github.com/warestack/bda/blob/main/team-project/README.md
Example corrected data:
timestamp | name | raw_text_vosk | text | time_taken_sec
2026-04-28T10:00:05 | Stelios | helo team today we discuss mobile app growth | Hello team, today we discuss mobile app growth. | 6.2
2026-04-28T10:00:18 | Mary | can we target students first | Can we target students first? | 3.8
2026-04-28T10:00:30 | Kate | i think we need lower pricing for early users | I think we need lower pricing for early users. | 5.1
Example enriched data:
timestamp values can be parsed as dates/times. Keep from the raw data. | Keep from the raw data. | AI-corrected transcript. | time_taken_sec is numeric and greater than 0. (Convert text to number?) Keep from the raw data. | question_flag contains boolean values. True if text ends with ?, otherwise False. | num_words is numeric and greater than 0. Number of words in text. | Number of characters in text. | speech_rate_wps is numeric and greater than 0. num_words / time_taken_sec, rounded sensibly. | speaker_turn_id is numeric and greater than 0. Running count for each speaker: first turn is 1, second turn is 2, etc.
timestamp | name | text | time_taken_sec | question_flag | num_words | text_size_chars | speech_rate_wps | speaker_turn_id
2026-04-28T10:00:05 | Stelios | Hello team, today we discuss mobile app growth. | 6.2 | FALSE | 8 | 47 | 1.29 | 1
2026-04-28T10:00:18 | Mary | Can we target students first? | 3.8 | TRUE | 5 | 29 | 1.32 | 1
2026-04-28T10:00:30 | Kate | I think we need lower pricing for early users. | 5.1 | FALSE | 9 | 46 | 1.76 | 1
2026-04-28T10:00:40 | Stelios | Ok, let's proceed! | 3.2 | FALSE | 3 | 18 | 0.94 | 2

## Requirements.txt
https://github.com/warestack/bda/blob/main/team-project/README.md
pandas>=2.0
requests>=2.31
vosk>=0.3.45
google-genai>=1.0
sounddevice>=0.4

## Moodle
https://moodle.bbk.ac.uk/mod/forum/discuss.php?d=291288
https://moodle.bbk.ac.uk/mod/forum/discuss.php?d=290976